## sheet1
21－2 三峡移民工程移民投资完成情况综合表（2011年底止）
Comprehensive Statistics on the Completed Investment in Three Gorges Resettlement (End of 2011)
单位：万元、% | (10 000 yuan, %)
指 标 | Item | 移民投资累计计划 | [5 empty] | 移民资金累计完成 | [11 empty] | 移民投资本年计划 | [5 empty] | 移民资金本年完成
|  | Cumulative Investment in Resettlement Planned | [5 empty] | Cumulative Investment in Resettlement Completed | [11 empty] | Investment in Resettlement Planned in Current Year | [5 empty] | Investment in Resettlement Completed in Current Year
|  | 小计 | 原概算投资 | 规划调整 新增投资 | 政策性 新增投资 | 一次性 补助投资 | 派 生 资 金 | 小计 |  | 原概算投资 |  | 规划调整 新增投资 |  | 政策性 新增投资 |  | 一次性 补助投资 |  | 派生资金 |  | 小计 | 原概算投资 | 规划调整 新增投资 | 政策性 新增投资 | 一次性 补助投资 | 派生资金 | 小计 |  | 原概算投资 |  | 规划调整 新增投资 |  | 政策性 新增投资 |  | 一次性 补助投资 |  | 派生资金
[8 empty] | total |  | Originally Estimated Investment |  | Additional Investment by Adjustment of Plan |  | Additional Investment by Policies |  | Lump-sum Subsidy Investment |  | Derived Funds | [7 empty] | total |  | Originally Estimated Investment |  | Additional Investment by Adjustment of Plan |  | Additional Investment by Policies |  | Lump-sum Subsidy Investment |  | Derived Funds
|  | Total | Originally Estimated Investment | Additional Investment by Adjustment of Plan | Additional Investment by Policies | Lump-sum Subsidy Investment | Derived Funds | 金额 | 比例 | 金额 | 比例 | 金额 | 比例 | 金额 | 比例 | 金额 | 比例 | 金额 | 比例 | Total | Originally Estimated Investment | Additional Investment by Adjustment of Plan | Additional Investment by Policies | Lump-sum Subsidy Investment | Derived Funds | 金额 | 比例 | 金额 | 比例 | 金额 | 比例 | 金额 | 比例 | 金额 | 比例 | 金额 | 比例
[8 empty] | Sum | Proportion | Sum | Proportion | Sum | Proportion | Sum | Proportion | Sum | Proportion | Sum | Proportion | [6 empty] | Sum | Proportion | Sum | Proportion | Sum | Proportion | Sum | Proportion | Sum | Proportion | Sum | Proportion
项目直接费合计 | Total of Direct Cost | 7032385.1247 | 4292048.8737 | 1444575.5052 | 792458.2196 | 166253.237 | 337049.2892 | 6697899.1017 | 95.2436 | 4241817.1167 | 98.8297 | 1269075.567 | 87.8511 | 703379.9422 | 88.7592 | 159021.8863 | 95.6504 | 324604.5896 | 96.3078 | 644968.1927 |  | 220599.49 | 424248.53 | 120.1727 |  | 534097.2191 | 82.8099 |  |  | 181088.1103 | 82.0891 | 352888.9388 | 83.1798 | 120.17 | 99.9977
农村移民安置 | Resettlement of Rural Residents | 2329363.5379 | 857669.678 | 752828.9322 | 577680.2878 | 77231.0566 | 63953.5834 | 2161034.5739 | 92.7736 | 849881.3682 | 99.0919 | 689869.6236 | 91.637 | 490685.6512 | 84.9407 | 72303.4464 | 93.6197 | 58294.4845 | 91.1512 | 503637.9957 |  | 81831.717 | 421686.11 | 120.1687 |  | 416478.8891 | 82.6941 |  |  | 65944.2503 | 80.5852 | 350414.4688 | 83.0984 | 120.17 | 100.0011
城市(县城)迁建 | Resettlement and Reconstruction of Cities | 2247557.796 | 1525517.6967 | 354962.1978 | 96972.118 | 27259.5429 | 242846.2406 | 2189914.9746 | 97.4353 | 1518327.2198 | 99.5287 | 306983.5199 | 86.4834 | 96641.8043 | 99.6594 | 26836.976 | 98.4498 | 241125.4546 | 99.2914 | 88114.33 |  | 88114.33 |  |  |  | 74658.72 | 84.7294 |  |  | 74658.72 | 84.7294
集镇迁建 | Resettlement and Reconstruction of Towns | 488622.1072 | 298171.9284 | 145747.3452 | 17410.0385 | 6972.496 | 20320.2991 | 444186.8936 | 90.906 | 290266.6157 | 97.3487 | 113216.3692 | 77.6799 | 17130.1485 | 98.3924 | 5707.896 | 81.863 | 17865.8642 | 87.9213 | 22253.343 |  | 21365.163 | 888.18 |  |  | 14056.02 | 63.1636 |  |  | 13255.79 | 62.0439 | 800.23 | 90.0977
工矿企业迁建 | Resettlement and Reconstruction of Industrial and Mineral Enterprises | 921561.788 | 829966.343 | 41855.99 | 3268.23 | 46384.475 | 86.75 | 909270.3287 | 98.6662 | 823515.3405 | 99.2227 | 36652.3842 | 87.5678 | 3068.23 | 93.8805 | 45947.624 | 99.0582 | 86.75 | 100 | 13186.33 |  | 13186.33 |  |  |  | 12203.42 | 92.546 |  |  | 12203.42 | 92.546
专业项目复建 | Reconstruction of Special Establishment | 679631.7756 | 507228.5256 | 67783.49 | 94701.88 | 6713.16 | 3204.72 | 665322.119 | 97.8945 | 502810.6367 | 99.129 | 61635.2393 | 90.9296 | 93603.2194 | 98.8399 | 6562.7436 | 97.7594 | 710.28 | 22.1636 | 2830.76 |  | 1156.52 | 1674.24 |  |  | 2830.76 | 100 |  |  | 1156.52 | 100 | 1674.24 | 100
环境保护 | Environmental Protection | 58272.5872 | 40889.5872 | 17383 |  |  |  | 52633.8784 | 90.3236 | 37553.9229 | 91.8423 | 15079.9555 | 86.7512 | [6 empty] | 11021 |  | 11021 |  |  |  | 10078.9 | 91.4518 |  |  | 10078.9 | 91.4518
勘测设计费 | Survey and Design Expense | 122795.2901 | 77966.5348 | 38521.27 | 2425.6653 | 198.67 | 3683.15 | 108084.9134 | 88.0204 | 76779.2957 | 98.4772 | 25309.9089 | 65.7037 | 2250.8888 | 92.7947 | 177.67 | 89.4297 | 3567.15 | 96.8505 | 169.29 |  | 169.29 |  |  |  | 169.29 | 100 |  |  | 169.29 | 100
监理费 | Supervision Expense | 52173.25 | 35739.1 | 16434.15 |  |  |  | 47481.4161 | 91.0072 | 35272.3127 | 98.6939 | 12209.1034 | 74.2911 | [6 empty] | 803.31 |  | 803.31 |  |  |  | 803.31 | 100 |  |  | 803.31 | 100
滑坡治理 | Landslide Control | 79671.02 | 75468.64 | 2955.73 |  | 1181.65 | 65 | 67621.5644 | 84.876 | 64918.9544 | 86.0211 | 1455.96 | 49.2589 |  |  | 1181.65 | 100 | 65 | 100 | 2951.83 |  | 2951.83 |  |  |  | 2817.91 | 95.4632 |  |  | 2817.91 | 95.4632
其他 | Others | 52735.9727 | 43430.84 | 6103.4 |  | 312.1865 | 2889.5461 | 52215.3766 | 99.0128 | 42958.49 | 98.9124 | 6063.4 | 99.3446 |  |  | 303.8802 | 97.3393 | 2889.6064 | 100.0021
注：此表投资统计口径含包干内项目直接费、政策性资金、派生资金以及规划调整新增资金。
Note: The statistics scope of investment in this table includes the direct cost of contracts, policy funds, derived funds and additional investment by adjustment of plan.